## 2018
Project Goals | Subcommitte Responsibilities | Key Activities | Timelines
|  |  | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-18 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
Collaborative Infrastructure | Nancy, Kathy & Deb | 1a. Organize a Coalition comprised of all agencies and individuals who can guide and sustain our plan | 2018-02-01: 2018-02-01; 2018-03-01: 9 Mar 2018First Meeting; 2018-05-18: Next Meeting 9 May 2018; 2018-07-01: See Meeting Minutes; 2018-09-01: See Meeting Minutes; 2018-11-01: See Meeting Minutes
| Subcommittee Community and Provider Education | 1 b. Education for Providers | 2018-05-18: Dr Barclay "Dementia" 3 May 2018; 2018-11-01: Dr. Nancy Miller 13 & 14 November 2018 ACD
| Deb(will be looking for volunteers) | 1c. Need of families w/ older adults in the community as an ongoing process | 2018-02-01: Mar-Jun 2018 - Subcommittee created to do one on one interviews with key personnel in the community
Database/Resource Materials | Need a subcommittee | 2a. Process to Identify Gaps in Existing Programs *** | 2018-02-01: Due June 2018 - Subcommittee formed to reach out to various organizations in the community to identify additional gaps in the community; 2018-12-01: Revisit Dec 2018
|  | 2b. Connect Resources base on community needs | 2018-02-01: Ongoing Develop Calendar of Events for mid August on issues within each community. Deb will work on a schedule to visit different communities. Nancy and Deb have presented at Cuyuna Women's Club. Nancy spoke at the Cuyuna Chamber of Commerce Event at Hallett Community Center. Suggestions: Local Churches, Libraries etc. This evolved into a subcommittee where different individuals visited with Fifty Lakes, Senior Center in Outing, City Clerks for Emily, Outing, Fifty Lakes, Deerwood, Ironton, and Crosby. This is still ongoing through 2019. Key areas identified is socialization, computer basics and food insercurity
Database/Resource Materials | Subcommittee Marketing Strategy/Public Relations | 2b.Part 1. Marketing Strategies Analysis Develop a Marketing Strategy for Events | 2018-02-01: Mar-Jun 2018 - This is still adhoc - developed Community Resource Guide for provider showcase
| Steering Committee | 2c. CMCOA and coalition revisit at Medical Staff of the Whole meeting - recap the project to create awareness and elicit needs to help promote wellness through the medical community | 2018-11-01: 2018-11-01
| Deb and Kathy and the Aging coalition resource task group | 2d. Strategies Connect Existing Resources - Prime list we can use is LSS and the CrowWing Energized Subcommittee on Aging Coalition Community Resources Task Group and our list | 2018-02-01: Ongoing Updates will be provided at each Meeting on the status of the list of resources - List of resources has been sent to press through Brainerd dispatch. December 2018. Tear out section for seniors listing relevant information
| Subcommittee Community Events | 2 e. Community Outreach "Getting to Know Your Neighbors" 20 Sponsors | 2018-05-18: Schedule for 19 May 2018 Tentative times 9 -1 pm Event was called Aging Wisely. Next Community event will be in 2019.
| Subcommittee Community Events | 2e. "Night with the Doctors" Coordination with Jennifer at events already scheduled | 2018-09-01: November was Provider Showcase for CRMC and Vendors from different services to interact with and learn what is available in the area. Community Resource Guide was created.
|  | 2e. Nancy, Kathy and Deb will present Silos to Circles Initiative at the Rural Health Conference | 2018-06-01: 6/26/2018 This was well received. Director of Health attended. Great questions from the audience.
| CMCOA Resource Task Group and Lutheran Social Services | 2f. Quick Reference Guide will be coordinated with 2.d and Minnesotahelp.info*** | 2018-07-01: Resource guide local completed Sep 2018; Resource guide tear out section for Seniors included in Brainerd Lakes Area Guide Dispatch sent to print in December 2018
Design & Implement Navigation Function for Sustainability | Deb and Subcommittee Building Partnerships and Sustainability | 3c. Explore Avenues for mininavigators within each community. | 2018-02-01: Ongoing Tentative Plan of Action Due by mid July 2018; This continues to be ongoing making sure we conduct one on one for each key community outreach and to build resilency. Have contact a variety of public services in the area, Churches, City Clerks, Police departments, Senior Centers, City Administrators and local businesses.
| Navigator | 3d. Will work with different community members to build networks withn the community that builds support for transportation, education aimed at eliminating isolation and independence. | 2018-02-01: Ongoing Updates in July and December of 2018; Continues to be ongoing phased into what would their role look like. Also looking at presenting at local events. First one will be the Expo in Crosslake.
| Steering Committee | 3e. Part 1: Develop a referral process with primary and acute providers to refer patients | 2018-08-01: ACD referral is in process working out some of the kinks in the steps of the process; Senior Linkage is continuing to be integral in consulting in the area and reaching the local senior population.
| Steering Committee | 3e.Part1a. Pilot project rolled out by provider champions. | 2018-09-01: Aug - Dec 2018; This will be accomplished at our next community event in May 2019
| Silos to Circles Committee | 3e. Part 2: Develop networks to build support in the community for transportation | 2018-07-01: Draft Due July 2018; There are several avenues for transportation all for fee or for specific purpose.
| Subcommittee Community and Provider Education | 3.e Part 3: Develop and coordinate education aimed at eliminating isolation and maintaining independence. | 2018-05-18: Draft Due May 2018; Programs have been developed through Community Education to assist people with variety of educational. The education is once a quarter. CMCOA has volunteered to provide training.
| Subcommittees Community Education/Community Events | 3e. Part 3a. Seniors Center without Walls (Amber Carroll Director )title changing to WellConnected | 2018-06-01: Subcommitte projected to meet with Amber in Jun Project will be Jun-Aug timeframe for Amber to conduct a program showcase to Heartwood Residents. Amber met with committee in November to demonstrate and explain the program. We have invited her back to present to the community.
| Subcommittee Building Partnerships and Sustainability | Create an infrastructure to Maintain Sustainability and Replicability | 2018-02-01: Ongoing

## 2019
Project Goals | Subcommittee Responsibilities | Key Activities | Timelines
|  |  | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01
Database/Resource Materials | Community Forum/Building Partnerships | 2a. Process to Identify Gaps in Existing Programs *** | 2019-01-01: Programs identified Isolation, Food Insecurity and Computers skills. Recommendfocus group to identify what the three different generations consider their needs; 2019-06-01: Revisit Jun 2019; 2019-12-01: Revisit Dec 2018
|  | 2b. Connect Resources base on community needs | 2019-01-01: Ongoing Develop Calendar of Events for mid August on issues within each community. Deb will work on a schedule to visit different communities. Nancy and Deb have presented at Cuyuna Women's Club. Nancy spoke at the Cuyuna Chamber of Commerce Event at Hallett Community Center. Suggestions: Local Churches, Libraries etc., There have been a variety of town events that we have been invited to participate in . Fifty Lakes, Emily Days etc.
| Deb and Kathy and the Aging coalition resource task group | 2b. Strategies Connect Existing Resources - Prime list we can use is LSS and the CrowWing Energized Subcommittee on Aging Coalition Community Resources Task Group and our list | 2019-01-01: Ongoing Updates will be provided at each Meeting on the status of the list of resources
| Steering Committee | 2d. Identify financial needs required to sustain ongoing efforts. | 2019-01-01: Jan - Mar 2019; 4 April 2019 Working on this do not have all the information on maintenance of website;
| Subcommittee Community Events | 2e. Explore holding 2 “Night with the Doctors” community events a year; hosted by CRMC and medical providers to highlight disease management. One event to be networking among the medical entities and the other will be community oriented | 2019-04-01: Crosslake Expo 27 Apr 2019; Created Flyer; Newsletter and Quick Reference Guide; 2019-05-01: Community Event May 2019; 2019-10-01: Provider Event Sep - Oct 2019
Design & Implement Navigation Function for Sustainability | Deb and Subcommittee Building Partnerships and Sustainability | 3c. Explore Avenues for mininavigators within each community. | 2019-01-01: Ongoing
Design & Implement Navigation Function for Sustainability | Steering Committee | 3e.Part1b. Implement and Monitor Referral processPilot project rolled out by provider champions. | 2019-01-01: Jan - Mar 2019; 2019-04-01: Apr- Dec Explore the potenital of Incorporation into EHR
| Subcommittee Building Partnerships and Sustainability | Create an infrastructure to Maintain Sustainability and Replicability | 2019-01-01: Ongoing
| Subcommittee Community Education |  | 2019-02-01: Healthy Hearts 21 Feb #36; 2019-04-01: Downsizing for Community; 2019-06-01: Polypharmacy for Providers